# Skyking Centralized CRM — Project Documentation & Implementation Blueprint

Version 0.1 (Draft for approval) · 7 October 2026

Prepared for Skyking leadership and the project steering group

What this document contains: (1) project documentation, (2) planning and roadmap, (3) system architecture and technical blueprint, (4) L1/L2/L3 escalation workflow and pan-India branch onboarding approach, and (5) implementation strategy. Per Key Decision 5, no development starts until the roadmap in Section 8 is signed off (Section 13).

# 1. Executive Summary

Skyking handles complaints today through a desktop CRM and phone calls between branches. There is no shared record, no clock on any complaint, and no way to see where a complaint is stuck. The proposal is a single, cloud-hosted CRM that every branch in India logs into, where each complaint has one record, one owner at a time, and a timer.

The core idea in one paragraph: complaints arrive from WhatsApp (via MSG91), email and branches, and land in L1. If L1 does not act within 6 hours the system escalates the complaint to L2 automatically (L1 can also escalate by hand). L2 investigates and assigns the complaint to the responsible branch. The branch works it and talks to the Head Office through a built-in chat window attached to the complaint. If nobody acts for another 6 hours it goes to L3, the final level. Every step is logged. Each branch onboards its own staff inside the CRM, and a branch can register a complaint itself and forward it to Head Office.

Important: we are not starting from zero. The CRM prototype you shared (FastAPI + React + PostgreSQL, with MSG91 ticket sync, an L0→L3 escalation state machine and a full audit trail) covers roughly the middle third of this system. The main new work is: branch multi-tenancy, automatic time-based escalation, email intake, branch staff onboarding, branch complaint registration and forwarding, the branch–Head Office chat, reporting, and production hardening.

Headline plan (planning estimate, to be validated in Phase 0): about 6 weeks to approve scope and design, about 5 months to a pilot-ready product, and about 8–9 months to have all branches live in waves.

# 2. Background, Objectives and Scope

## 2.1 Problem

- Complaints are coordinated over phone calls between branches, so they are delayed, lost or duplicated.

- Branches are not on a common platform; Head Office cannot see branch-level status.

- The existing desktop CRM has no structured resolution process, so there is no tracking, ageing or accountability.

## 2.2 Objectives

- One centralized platform onto which every branch in India can be onboarded.

- End-to-end complaint handling: registration, assignment, tracking, escalation, resolution and closure.

- Time-bound escalation through L1, L2 and L3, with a 6-hour unattended trigger.

- Phone-call coordination replaced by in-system communication between branches and Head Office.

- A complete, approved roadmap before any development begins.

## 2.3 Scope

| In scope (Release 1) | Out of scope / later |
| --- | --- |
| Complaint intake from WhatsApp (MSG91), email, and manual creation by Head Office agents (phone calls) or branch staff | Voice-call (IVR/telephony) integration |
| L1/L2/L3 workflow with manual and automatic escalation | Customer self-service portal or mobile app |
| Branch assignment, branch work queue, branch–Head Office chat | Integration with a booking/consignment-tracking system (design allows it; see Open Decisions) |
| Branch and staff onboarding, roles and permissions | AI-based auto-classification or reply suggestions (candidate for Release 2) |
| Dashboards, reports, export, notifications, audit trail | Full migration of all historical data from the desktop CRM (open complaints and customer master only; see 9.5) |

## 2.4 Key Decisions (from the brief)

| # | Decision |
| --- | --- |
| 2 | CRM designed so all branches across India can be onboarded onto one centralized platform. |
| 3 | End-to-end complaint resolution: registration, assignment, tracking, escalation, resolution, closure. |
| 4 | Time-bound escalation levels L1, L2, L3. |
| 5 | Complete, approved planning and development roadmap before development begins. |

Note: the brief we received lists decisions 2–5; decision 1 was not included. Please confirm whether something is missing.

Additional requirements stated in the brief and treated as binding: L2 assigns complaints to the respective branch; branches get a window to talk to Head Office; unattended complaints escalate after 6 hours; L1 complaints come from email, MSG91 APIs, WhatsApp and similar channels; a branch can onboard its own staff in the CRM; a branch can register a complaint it receives and forward it to Head Office, where L1, L2 and L3 sit.

## 2.5 Assumptions (please correct any that are wrong)

- L1, L2 and L3 are Head Office teams. Branches are a separate group of users who receive assigned work; they are not an escalation level.

- The number of branches, staff per branch and complaint volume are not yet known. The design assumes hundreds of branches and thousands of complaints per day as an upper planning bound; Phase 0 replaces this with real figures.

- MSG91 remains the WhatsApp channel provider. Email arrives in a dedicated Skyking complaints mailbox.

- Branch staff may use low-end devices and variable internet, so the branch interface must work well on a phone browser.

- Hosting in an Indian cloud region is acceptable.

# 3. Current State: What the Prototype Gives Us

We reviewed the uploaded code (backend and frontend). Summary of fit against the new requirements:

| Capability | Prototype today | Gap for the new scope |
| --- | --- | --- |
| MSG91 WhatsApp ticket sync | Polls every 60s; filters by origin, inbox id 2271, team id 2253 (stored in a config table); de-duplicates on MSG91 ticket id | Endpoint paths unverified against live MSG91 docs; full message history not wired; single inbox only; polling rather than webhooks |
| Roles and escalation | Roles admin, support (L0), L1, L2, L3; one level at a time; Admin can force a skip; role-gated actions | No time-based escalation; L0 vs L1 does not match the brief (see 5.1); no branch roles |
| Audit trail | Append-only ticket_history on every action; per-hop escalations table | Keep as is; extend with trigger type (manual / automatic) |
| Customers and consignments | Customer and consignment tables, linked to tickets | Fine for Release 1; no booking-system link |
| Branches | None | Entire branch model, assignment, scoping and onboarding are new |
| Email intake | None | New |
| Branch–Head Office chat | None (ticket comments exist, but are per-level notes) | New |
| Dashboards | Role-specific counts | Add ageing, SLA breach, branch performance, filters |
| Reports and export | Not built | New |
| Staff management | Users table only; no admin UI or endpoints | New: invitations, approval, deactivation, password reset |
| Migrations and deployment | create_all on startup; no Alembic | Needs migrations, CI/CD, environments |
| Frontend | A localStorage-only demo build (no real login, data not shared) | Demo only. Production frontend must run against the backend API |

## 3.1 Issues to fix before building on it

- Secrets and credentials: a default SECRET_KEY and a seeded admin password (ChangeMe123!) are in the code and README. These must never reach a production environment; use secret storage and forced password change.

- Complaint number generation: the CRM code is generated as count of tickets plus one. Two simultaneous syncs can produce duplicates. Use a database sequence.

- Scheduler: APScheduler runs inside the web process. With more than one server instance the sync would run twice. Move to a dedicated worker with a queue and job locking.

- Close permission: only L3 or Admin may close. At national scale this becomes a bottleneck; we recommend L2 can close non-critical complaints (Open Decision 6).

- Authentication: 12-hour JWT with no refresh or revocation. Add refresh tokens, session revocation and MFA for admins.

# 4. Functional Requirements Summary

| Module | Key requirements |
| --- | --- |
| Registration | Auto-create complaint from WhatsApp and email; manual entry by L1 or branch, including phone-call complaints (see 5.6); unique complaint number; match or create customer by mobile and email; capture consignment number, receiver details, address and pincode; attachments (photos, PDFs); duplicate detection; acknowledgement to the customer |
| Assignment | L1 queue with pick-up; L2 assigns to a branch (optionally a named staff member); suggested branch from pincode mapping; reassign by L2 and Admin |
| Tracking | Single status and owner at all times; customer-facing and internal notes kept separate; complete timeline; search and filters (status, level, branch, priority, age, channel, date) |
| Escalation | Manual escalation with mandatory reason; L2 can assign to a branch with a custom deadline or escalate directly to L3; de-escalation (L3 to L2, L2 to L1) with mandatory reason and handover note; automatic escalation when unattended 6 hours (configurable); warnings before breach; L3 breach alert |
| Branch window | Chat thread on each complaint between branch and Head Office; general branch help-desk channel; attachments; notifications |
| Branch registration | Branch staff register a complaint, save as draft, and forward to Head Office (L1 queue); branch sees status of everything it forwarded |
| Resolution and closure | Resolution form (root cause, action taken, outcome); customer confirmation message; reopen window; closure rules |
| Onboarding | Branch master; Branch Admin invites staff; role limited to branch scope; Head Office approval optional; deactivate leavers |
| Reporting | Role-specific dashboards; SLA, ageing, branch league table, repeat-complaint view; Excel and PDF export |
| Administration | Configurable SLA policies, escalation rules, working hours, categories, templates; audit log of config changes |

# 5. L1 / L2 / L3 Escalation Workflow

## 5.1 Level definitions

| Level | Who | Responsibility | Can do | Cannot do |
| --- | --- | --- | --- | --- |
| L1 (first level) | Head Office support desk. Receives every complaint from WhatsApp, email, manual entry (phone calls) and branch forwarding | Acknowledge, collect missing details (consignment, receiver, address), attempt first-contact resolution, categorize | Pick, comment, message customer, resolve simple cases, escalate to L2 | Assign to a branch; close |
| L2 (second level) | Head Office operations / supervisors | Investigate, identify the responsible branch, assign the complaint to that branch, follow up with the branch, verify the branch’s action | Assign and reassign to branches, chat with branch, resolve, close non-critical, escalate directly to L3 at any time, set and extend branch deadlines (see 5.7), send back to L1 (de-escalate, see 5.8) | Override SLA settings |
| L3 (final level) | Senior management / escalation head | Decide on complaints that L2 and the branch could not close in time; handle critical and repeat complaints | Take over, reassign, resolve, close, force decisions, send back to L2 (de-escalate, see 5.8) | Escalate further (breach triggers management alert instead) |
| Branch staff | Branch users (not a level) | Register branch complaints and forward them; acknowledge, fix the issue on the ground, update status, talk to Head Office | Work only complaints assigned to or originated by their branch | See other branches’ complaints |
| Admin | System administrators | Configuration, users, branches, reports | Everything, including forced level skip (audited) | n/a |

Note on the prototype’s L0: the prototype has a separate L0 (Support) before L1. The brief defines L1 as the first level. We recommend merging L0 into L1 (L1 agents plus an optional L1 team lead) so there are exactly three levels. This is Open Decision 1.

## 5.2 Complaint lifecycle

REGISTERED → L1 QUEUE → L1 WORKING ──resolve──┐
                │ (6h unattended or manual)    │
                ▼                              │
            L2 QUEUE → L2 REVIEW ──resolve─────┤
                │ assign to branch             │
                ▼                              │
        ASSIGNED TO BRANCH → BRANCH ACKNOWLEDGED → ACTION TAKEN
                │ (6h unattended)              │
                ▼                              ▼
            L3 QUEUE → L3 WORKING ───────→ RESOLVED → (customer confirms / window passes) → CLOSED
                                                │ customer disputes
                                                └────→ REOPENED (returns to the level that resolved it, or L2)

Statuses: Draft (branch only), Registered, L1 Queue, L1 Working, L2 Queue, L2 Working, Awaiting Branch Info, Assigned to Branch, Branch Acknowledged, Action Taken (awaiting verification), L3 Queue, L3 Working, Awaiting Customer, Resolved, Closed, Reopened.

## 5.3 Time-bound escalation rules

What counts as unattended. A complaint is unattended when either (a) it sits in a level’s queue and nobody has picked it up, or (b) it is picked up but no action is logged: no status change, no comment, no customer message, no branch update. Any logged action resets the timer. While the status is Awaiting Customer the timer is paused.

| Rule | Default (configurable by Admin) |
| --- | --- |
| Unattended threshold at L1 | 6 hours → auto-escalate to L2 |
| Unattended threshold at L2 (including after assigning to a branch and the branch not acknowledging) | 6 hours → auto-escalate to L3 |
| Branch acknowledgement threshold | 6 hours by default, or the deadline L2 sets when assigning (within Admin limits, proposed 2 to 48 hours) → auto-escalate to L3 and notify L2. Admin can change the action to alert L2 only |
| Early warning | At 80% of the threshold: notify the owner and the team lead |
| Critical priority | Proposed 2-hour threshold (for confirmation) |
| Manual escalation | Allowed at any time, reason mandatory. L1 escalates to L2; L2 can escalate directly to L3, with or without a branch assignment |
| L3 breach | No higher level; alert Admin and named management contacts, repeat every 6 hours until acted on |
| Clock | Proposed: working hours (e.g. Mon–Sat, 9:00–19:00 IST) so complaints do not all escalate overnight. Option: 24×7. Open Decision 2 |
| Skipping levels | Admin only, always audited |

Each auto-escalation is written to the audit trail as triggered by the system, with the rule that fired, and a notification goes to the previous owner, the next level and the team lead.

## 5.4 Branch assignment and the branch–Head Office window

- Branch suggestion. The consignment’s pincode and origin or destination are matched to a branch serviceability map. L2 sees a suggested branch and can accept or override.

- Assignment. L2 assigns to a branch queue or to a specific staff member. The Branch Admin can redistribute within the branch.

- Branch work. The branch acknowledges, updates progress and records the action taken. Branch staff only see complaints assigned to their branch.

- The window. Each complaint has a Head Office thread between the branch and L1/L2/L3 handling it: messages, photos, documents, read receipts and notifications. It is internal; customers never see it. Separately, each branch has a general Help Desk channel to Head Office for questions not tied to one complaint.

- Complaints that start at the branch (customer walks in or phones the branch): branch staff register the complaint in the CRM with source Branch. It enters L1 tagged to that branch, with its Head Office thread open from the start, so the conversation moves from phone calls into the system. The full register-and-forward mechanism is in 5.5.

- Verification. When the branch marks Action Taken, L2 verifies before the complaint moves to Resolved.

## 5.5 Branch-registered complaints: register at the branch, forward to Head Office

When a customer walks in or phones a branch, branch staff register the complaint in the CRM themselves and forward it to Head Office, where it enters the L1 → L2 → L3 chain. The branch no longer relays it by phone.

- Register. Branch staff choose New Complaint. Branch, staff name and time are filled in automatically. They enter the customer’s mobile (existing customers are matched and shown, with any open complaints), the issue description, category, consignment number, receiver name, receiver mobile and delivery address with pincode, and attach photos or documents.

- Complaint number at once. The CRM issues the complaint number on registration so the branch can give it to the customer immediately. The customer also receives an acknowledgement on WhatsApp or SMS.

- Forward to Head Office. One button, Forward to Head Office, sends it to the L1 queue with source Branch and the originating branch recorded. A branch can save a Draft first; drafts are visible only to that branch and are not tracked by SLA until forwarded. The default action on the form is Register and Forward.

- Head Office thread opens automatically so the branch and L1 can talk about the complaint in the system from the first minute.

- Normal workflow from here. The 6-hour L1 clock starts at the moment of forwarding. L1 works it or escalates to L2; L2 may assign it back to the originating branch or to a different one; L3 is the final level (Sections 5.3 and 5.4).

- Branch visibility. The originating branch can always see the status, current level, owner and timeline of every complaint it forwarded (read-only), and gets a notification at each stage change.

| Situation | What the system does |
| --- | --- |
| Urgent or high-value complaint | Branch can flag it Urgent. L1 and L2 team leads are alerted immediately. Priority is confirmed by L1. |
| Customer already has an open complaint for the same consignment | Warns the branch and offers to attach the new details to the existing complaint instead of creating a duplicate. |
| Head Office needs more information | L1 returns it to the branch with a question (status Awaiting Branch Info). The L1 clock pauses; a separate 6-hour response limit alerts L2 if the branch stays silent. |
| Branch has weak connectivity | The form is saved on the device and submits automatically when the connection returns; the branch sees Pending Upload until then. |
| Branch staff forwards by mistake | Can withdraw only while L1 has not yet picked it up; afterwards they ask L1 in the Head Office thread. |
| Complaint should skip L1 | Not allowed by default. An Admin rule can let specific categories go straight to L2 (Open Decision 14). |

Every action (registered by, forwarded by, forwarded at, withdrawn, returned for information) is written to the audit trail. Branch staff can only register complaints for their own branch.

## 5.6 Manual ticket creation by agents (phone calls and other offline complaints)

Not every complaint arrives by WhatsApp or email. Many customers call. The CRM therefore lets an agent create a complaint manually while the customer is on the line, or immediately after the call, so that nothing lives only in someone’s memory or notebook. No telephony integration is needed for this in Release 1.

Who can create: L1 agents (the default), L2, L3 and Admin at Head Office. Branch staff use the register-and-forward flow in 5.5. A complaint created at L2 or L3 is logged at that level and the creation is audited.

- Start. The agent clicks New Complaint (available on every screen) and picks the source: Phone call (inbound), Phone call (callback by Skyking), Walk-in (via branch), or Other (letter, social media, in person).

- Find the customer while on the call. Search by mobile number, email or consignment number. If the customer exists, their details and any open or past complaints are shown, so the agent can tell the caller about an existing complaint instead of creating a duplicate. If not found, the agent creates the customer inline with name and mobile.

- Capture the complaint. Required to save: customer mobile, category and description. Strongly requested: consignment number, receiver name and mobile, delivery address with pincode, priority, and preferred contact method and language. Optional call details: caller number, time of call, and a call reference (for example a call-recording ID typed in by the agent).

- Duplicate check. If the same customer already has an open complaint on the same consignment, the CRM warns the agent and offers to add the call as a note on that complaint.

- Save. The complaint number is issued immediately so the agent can read it out to the caller. An acknowledgement goes to the customer by WhatsApp or SMS.

- Ownership choice. The agent either takes the complaint (Assign to me; the L1 clock starts as picked up) or sends it to the L1 queue for someone else. Normal timers and escalation (5.3) apply from the moment of saving.

- Resolve on the call, if possible. If the issue is settled during the call, the agent saves with Resolved on first call and completes the short resolution form (action taken, outcome). The complaint then follows the normal confirmation and closure rules.

- Callbacks and follow-ups. The agent can schedule a callback date and time with a reminder, and add notes after each call. Customer follow-ups that arrive later by WhatsApp or email attach to the same complaint number.

- Missing details. If the agent saves with incomplete details, the complaint is marked Incomplete and L1 must complete consignment and pincode before it can be assigned to a branch.

| Control | Rule |
| --- | --- |
| Source tracking | Every complaint records how it was created (WhatsApp, email, phone inbound, phone callback, walk-in, branch, other), who created it, and when. Reports show the phone share of volume. |
| SLA start | The clock starts at the moment the ticket is saved in the CRM, not at the time of the call, so late data entry cannot hide delay. The call time is stored separately for reporting. |
| Editing | The original description cannot be overwritten after saving. Agents add notes or corrections; every change is audited. |
| Duplicates | Agents or L2 can merge duplicate complaints; the merge keeps both histories. |
| Branch-related calls | If the caller names a branch, the agent records it; L2 still decides the branch assignment (5.4). |
| Future option | A later release can add click-to-call and screen-pop (customer record opens on an incoming call) if Skyking uses a telephony system; the manual form stays as the fallback. |

## 5.7 What L2 can do with a complaint

L2 has three ways to move a complaint forward and chooses per complaint. L2 can also let the clock decide: if L2 does nothing, the complaint goes to L3 automatically after the specified time.

| L2 option | What happens | Timer |
| --- | --- | --- |
| Resolve at L2 | L2 completes the resolution form; normal confirmation and closure rules apply. | Complaint leaves the escalation clock. |
| Assign to a branch | The complaint goes to the branch queue or a named staff member, and the Head Office thread opens. L2 sets a deadline for the branch when assigning (default 6 hours; Admin sets minimum and maximum limits, proposed 2 to 48 hours). L2 keeps supervising it. | Branch deadline. If the branch has not acknowledged or acted by then, the complaint escalates to L3 automatically and L2 is notified. Admin can instead set this action to alert L2 only. |
| Escalate to L3 | At any time, with a mandatory reason, with or without a branch assignment. L3 becomes the owner. If a branch was involved it stays in the thread and can keep updating, unless L3 reassigns. | L3 clock starts. |
| Take no action | Nothing is lost: the complaint stays in the L2 queue. | After the L2 threshold (default 6 hours) it escalates to L3 automatically. |

- Extending a deadline. Before a deadline passes, L2 can extend it with a reason (for example the branch reports the parcel is in transit). Every extension is logged, and Admin limits the number of extensions per complaint (proposed 2).

- Different times for different cases. Default and limit times can be set per priority and complaint category, so a critical complaint can have a shorter branch deadline than a routine one.

- Warnings. At 80% of any deadline the owner and team lead are notified, as in 5.3.

- Every one of these actions, including automatic escalations and extensions, is written to the audit trail with who or what triggered it.

## 5.8 De-escalation: sending a complaint back down

A complaint sometimes reaches a level too early, or the higher level has decided and the lower level must carry it out. The CRM therefore has a controlled reverse path: L3 → L2 and L2 → L1.

| Direction | Who can do it | Typical reasons |
| --- | --- | --- |
| L3 → L2 | L3 users and Admin | Escalated too early; needs branch follow-up; L3 has decided and L2 must execute; priority reduced |
| L2 → L1 | L2 users and Admin | Customer details missing; wrong category; customer must be contacted again; can be settled at first level |
| Branch → Head Office (return, not a level) | Branch staff | Wrong branch; branch cannot act; needs a Head Office decision. Goes back to L2 with a reason. |
| L3 → L1 (skip) | Admin only | Exceptional; always audited |

Rules

- Send back button. Available on a complaint the person currently owns or supervises, as Send back to L2 (at L3) or Send back to L1 (at L2).

- Reason and handover note are mandatory. The sender picks a reason (Escalated too early, More information needed, Wrong category or branch, Action needed at lower level, Decision taken and needs execution, Priority reduced, Other) and writes a handover note of at least 20 characters telling the receiving level what to do. It cannot be saved without both.

- Destination. By default the complaint returns to its previous owner at that level if still active, otherwise to that level’s queue. The sender can choose a named person instead.

- Fresh clock. The receiving level starts a full threshold (default 6 hours) at the moment of sending back, so the complaint is not re-escalated at once. The complaint’s total age keeps counting, and the time spent at each level is recorded and shown.

- Branch involvement. Sending back L3 → L2 leaves the branch in the thread and L2 resumes supervising. Sending back L2 → L1 with an active branch assignment requires the sender to choose: withdraw the assignment (branch notified, thread becomes read-only) or keep it.

- Visibility. The complaint shows a banner: sent back from L3 by name, reason, note. The receiving team lead and the previous owner are notified, and the full history is visible to all levels handling it.

- Cooling rule (no hot potato). A complaint that was just sent back cannot be manually escalated again until the receiving level has logged at least one action. The automatic timer still applies, so nothing can sit unattended.

- Bounce limit. A complaint can be sent back at most 2 times (configurable). When it has changed level 4 times in total it is flagged Repeated movement, the team lead and Admin are alerted, and any further send-back needs Admin approval.

- Not allowed on Draft, Resolved or Closed complaints. Use Reopen for those (5.5).

- Reporting. Reports show send-backs by direction, reason and person, to spot poor triage or premature escalation.

## 5.9 Complete transition rules and system guarantees

The workflow is a strict state machine: a complaint can only move by the transitions below. Anything not listed is rejected by the server, whatever the screen shows.

| From → To | Who / trigger | Reason needed | Timer effect |
| --- | --- | --- | --- |
| Draft → L1 Queue | Branch staff forward (5.5) | No | L1 clock starts |
| New (WhatsApp, email, phone, manual) → L1 Queue | System or agent on save | No | L1 clock starts |
| L1 Queue → L1 Working | L1 agent picks up (locked, one person only) | No | Clock resets on each logged action |
| L1 → L2 | L1 manual, or automatic when unattended (default 6h) | Manual: yes. Automatic: rule recorded | L2 clock starts |
| L1 / L2 / L3 → Resolved | Owner completes resolution form | Yes (resolution form) | Clock stops |
| L2 → Assigned to Branch | L2 | Branch and deadline | Branch deadline starts |
| Assigned to Branch → Branch Acknowledged → Action Taken | Branch staff | Notes on action | Deadline satisfied; L2 verification clock starts |
| Assigned to Branch → L3 | Automatic at branch deadline (default 6h) | Rule recorded | L3 clock starts; L2 notified |
| Branch → L2 (return) | Branch staff | Yes | Fresh L2 clock |
| L2 → L3 | L2 manual, or automatic when unattended (default 6h) | Manual: yes | L3 clock starts |
| L3 → L2 (de-escalate) | L3 or Admin | Reason and handover note | Fresh L2 clock |
| L2 → L1 (de-escalate) | L2 or Admin | Reason and handover note | Fresh L1 clock |
| Any working state → Awaiting Customer or Awaiting Branch Info | Owner | Yes | Clock paused; resumes on reply; separate limit on Awaiting Branch Info |
| Resolved → Closed | Customer confirms, or auto-close after the set period, or L2/L3 per closure rules | No | Stops |
| Resolved or Closed → Reopened | Customer reply within the window, or L2/Admin | Yes | Goes to the level that resolved it, or L2, with a fresh clock |
| Any → any (forced) | Admin only | Yes | Audited as admin_force |

Guarantees the system enforces (and tests must prove)

- One owner, one level. At any moment a complaint has exactly one owning level and one status. Two people acting at once cannot both win: the second gets a clear message that the complaint has already changed.

- Nothing without a clock. Every non-terminal complaint either has a running timer or is in a named paused state with a defined way to resume. L3 has no higher level, so an L3 breach alerts management repeatedly until acted on.

- Every move is recorded with the move. The status change and its history entry (who or what, from, to, reason, time) are saved in one database transaction, so one cannot exist without the other. History is append-only and cannot be edited, even by Admin.

- Server decides, not the screen. Permissions, branch scope and timers are checked on the server using server time (UTC), never the user’s device clock.

- No complaint is orphaned. If an owner is deactivated, goes on leave or a branch is suspended, their open complaints return to the level’s queue or the Branch Admin and the team lead is alerted.

- No silent failure. The automatic escalation scanner is safe to run twice, reports a heartbeat, and pages the technical team if it stops. A separate daily reconciliation job lists complaints with no owner, no timer, or no activity beyond a set age, and alerts Admin.

- Customer messages never lost. WhatsApp and email intake is de-duplicated and retried; failures go to a dead-letter queue that is monitored.

- Test coverage. Every row of the table above has an automated test, including the rejected transitions, simultaneous actions, the cooling rule and the bounce limit.

## 5.10 Rules and edge cases

- One owner at a time; pick-up is first come, first served and is locked so two people cannot take the same complaint.

- Customer replies on WhatsApp or email attach to the existing open complaint, not a new one. A reply after Resolved reopens it within a configurable window (proposed 7 days).

- Priority is set by L1 on triage using category rules (for example lost consignment, damaged high-value goods) and can be raised by any level.

- Leave and shift cover: Admin or team lead can bulk-reassign a user’s open complaints.

- All timers use IST for display and UTC in storage.

# 6. System Architecture and Technical Blueprint

## 6.1 Design principles

- Evolve the prototype, do not rewrite it. Keep FastAPI, PostgreSQL, React and the escalation service; add what is missing.

- Modular monolith first. One deployable backend with clear internal modules (intake, workflow, SLA, branches, chat, reporting). Microservices add cost and failure modes that a team this size does not need. Modules can be split later.

- One database, branch-scoped rows. Every complaint carries a branch id; access is enforced in the API layer, not by separate databases per branch.

- Channels are plug-ins. WhatsApp, email and manual entry all feed the same normalized complaint record through an adapter.

- Rules are data, not code. SLA thresholds, working hours, priorities, categories and the MSG91 inbox and team ids live in configuration tables editable by Admin (the prototype already does this for MSG91 ids).

- Everything is audited. Append-only history for every action, including those taken by the system.

## 6.2 Logical architecture

CHANNELS                    PLATFORM (India cloud region)                        USERS
WhatsApp (MSG91) ─webhook/poll─┐
Email mailbox  ──IMAP / mail API┤   ┌─ API (FastAPI) ── auth, RBAC, branch scoping ──┐
Manual entry (HO / branch) ────┤──▶│  Intake · Workflow · Branches · Chat · Reports   │◀── React web app
                                │   └── WebSocket / SSE for live chat & queues      │     (HO + branch, mobile-ready)
                                ├─ Worker (queue) ── channel sync, SLA scanner, notifications
                                ├─ PostgreSQL ── system of record + audit
                                ├─ Redis ── job queue, locks, pub/sub, cache
                                └─ Object storage ── attachments, email bodies, exports
NOTIFICATIONS: email · WhatsApp template (MSG91) · in-app · SMS   MONITORING: logs, metrics, alerts

## 6.3 Technology choices

| Layer | Choice | Reason |
| --- | --- | --- |
| Backend | Python, FastAPI, SQLAlchemy 2 (existing) | Already built and working; keep |
| Database | PostgreSQL (managed) | Already the target; strong for relational data, row locking, JSON |
| Migrations | Alembic (already in requirements) | Replace create_all before any shared environment |
| Queue and scheduler | Redis with a worker (Celery, RQ or Arq) | Runs SLA scanner and syncs outside the web process; safe with multiple instances |
| Real-time | WebSocket or Server-Sent Events | Live chat and queue refresh |
| Frontend | React + Vite (existing), responsive and installable as a PWA | Branch staff on phones; no app-store dependency |
| Files | S3-compatible object storage | Attachments and exports out of the database |
| Hosting | Managed cloud in an Indian region (for example AWS Mumbai), containers, managed Postgres and Redis | Latency and data residency; low operations load |
| Observability | Central logs, metrics, uptime and error alerts | Know about failures before branches do |

The final cloud provider and exact queue library are decisions for Phase 0; the structure above does not depend on them.

## 6.4 Branch multi-tenancy and access control

Hierarchy: Organization → Region/Zone → Branch → Staff. Roles are combined with a scope:

| Role | Scope | Typical permissions |
| --- | --- | --- |
| Super Admin | All | Configuration, branches, all users, all data |
| HO Admin | All | Users, branches, reports, reassignment |
| L1 / L2 / L3 | All branches (optionally limited to regions) | Level-specific actions per Section 5.1 |
| Regional Manager (optional) | One region | Read-only view of branches in the region |
| Branch Admin | One branch | Invite and deactivate staff, redistribute complaints, register and forward complaints, chat with HO |
| Branch Staff | One branch | Work assigned complaints, register and forward branch complaints, chat with HO |

Enforcement: every query on complaints, chat and customers is filtered by the user’s scope in one shared function, and automated tests prove a branch user can never read another branch’s data.

## 6.5 Data model changes

The existing tables (users, roles, customers, consignments, msg91_tickets, msg91_messages, tickets, ticket_comments, escalations, ticket_history, system_config) are kept. Additions:

| Table / change | Purpose |
| --- | --- |
| regions, branches | Branch code, name, city, state, address, status, region, contact; branch–pincode serviceability map |
| users (add branch_id, mobile, status, last_login) | Branch scoping; status values invited, active, suspended |
| staff_invitations | Branch Admin invites by mobile or email; token, role, expiry, approver, accepted time |
| tickets (add branch_id, origin_branch_id, registered_by, forwarded_at, call_received_at, caller_number, call_reference, source, category_id, sla_due_at, level_entered_at, last_activity_at, paused_at, reopen_count, escalation_count, deescalation_count, last_moved_at) | Branch assignment, originating branch, source channel, timers |
| escalations (add trigger: manual, auto_sla, admin_force, branch_breach, l2_direct; direction up or down; reason_code; handover_note; rule_id) | Distinguish human from automatic escalation |
| sla_policies | Threshold per level and priority, working-hours calendar, warning percentage, active flag |
| working_calendars, holidays | Business-hours clock |
| channel_accounts, email_messages | Mailbox settings; raw email with Message-ID and In-Reply-To for threading |
| conversations, conversation_messages, message_reads | Complaint-level HO thread and branch Help Desk channel; internal only |
| attachments | Metadata for files in object storage; virus-scanned |
| notifications | In-app and outbound notification log with delivery status |
| categories | Complaint types, default priority and default branch-assignment hints |
| audit_log | Admin and configuration changes, logins, permission changes (separate from ticket_history) |
| ticket status enum | Extend with Draft (branch only), Forwarded to HO, Awaiting Branch Info, Assigned to Branch, Branch Acknowledged, Action Taken, Awaiting Customer, Reopened |

Complaint numbers move from count-plus-one to a database sequence (format CRM-0000125 retained).

## 6.6 Complaint intake design

WhatsApp via MSG91. Keep the adapter in msg91_client.py. Before building on it: (a) confirm endpoint paths and parameters against the live MSG91 Hello documentation and the Skyking account, (b) ask MSG91 whether event webhooks are available for new tickets and messages, which would replace the 60-second polling with near-real-time delivery (keep a slower poll as a safety net), (c) wire in full message history, (d) support more than one inbox and team through configuration. Customer replies from the WhatsApp thread attach to the open complaint.

Email. A dedicated complaints mailbox is read by the worker (IMAP or the mail provider’s API). Each email becomes a complaint or, if it carries a known complaint number or In-Reply-To header, a reply on an existing one. Attachments go to object storage. Auto-replies, bounces and spam are filtered. Replies sent from the CRM go out from the same mailbox so threads stay intact.

Manual. L1 agents and other Head Office users create complaints by form for phone calls and other offline cases (Section 5.6); branch staff register walk-in cases and forward them (Section 5.5). A branch registration is forwarded to the L1 queue as described in Section 5.5.

Normalization. All channels produce the same record: customer, channel, subject, body, attachments, consignment fields if present, received time. L1 completes missing consignment and address details; the WhatsApp bot already asks customers for these.

## 6.7 SLA and auto-escalation engine

- Each complaint stores sla_due_at, computed from the active policy, the current level and the working-hours calendar.

- A scanner job runs every minute, selects complaints whose due time has passed using row locking (SELECT … FOR UPDATE SKIP LOCKED), and calls the same escalate function used for manual escalation with trigger set to auto_sla. One code path means one set of rules and one audit format. When L2 sets a custom deadline on a branch assignment, it is stored as the complaint’s due time within Admin-set minimum and maximum limits (and a capped number of extensions), and the scanner treats it like any other due time.

- Warning notifications fire at 80% of the threshold. When a complaint is de-escalated the receiving level starts a fresh full clock, and the cooling rule in 5.8 stops it bouncing between levels. Timers pause at Awaiting Customer and Awaiting Branch Info and resume on reply.

- The scanner is idempotent: running twice never escalates twice. Tests cover boundaries, working-hours edges, holidays and clock skew.

- If the scanner stops, a heartbeat alert pages the technical team, because a silent failure here is the most damaging failure in the system.

## 6.8 Branch–Head Office chat

Messages are stored in conversation_messages, delivered live over WebSocket or SSE, and fall back to in-app and email or WhatsApp notification when the recipient is offline. Visibility is limited to the branch involved and the Head Office levels handling the complaint. Photos and documents upload to object storage. Messages cannot be edited after sending; deletions are soft and audited.

## 6.9 API surface (additions)

Branches and regions (CRUD, serviceability); staff invitations and acceptance; users (list, suspend, reset); manual complaint creation by agents with customer lookup; branch complaint registration, save-as-draft, withdraw and forward to Head Office; complaint assignment to branch; branch acknowledge and action-taken; conversations and messages; SLA policies and calendars; reports and exports; notification preferences; webhooks (MSG91 and email provider). All endpoints are versioned under /api/v1 and documented through the auto-generated OpenAPI spec.

## 6.10 Security and compliance

- Password hashing (bcrypt, existing), refresh tokens, session revocation, login throttling, MFA for Admin and HO roles, OTP or email-link sign-in for branch staff.

- TLS everywhere, encrypted database and storage, secrets in a secret manager (the MSG91 auth key stays server-side only, as in the prototype).

- Customer data includes names, mobile numbers, addresses and consignment details. India’s Digital Personal Data Protection Act, 2023 applies to this kind of data; we recommend Skyking’s legal adviser confirms consent wording, retention periods and breach-notification duties before launch.

- Daily backups with tested restore; proposed targets: recovery point 15 minutes, recovery time 4 hours.

- Role-based export controls and an audit log of who exported what.

- Penetration test before pilot.

## 6.11 Non-functional targets (proposed)

| Area | Target |
| --- | --- |
| Availability | 99.5% monthly during working hours |
| Page response | Under 2 seconds for common screens at normal load |
| Concurrency | Sized from Phase 0 figures; load tested at 3× expected peak |
| Devices | Current Chrome, Edge, Safari; Android and iOS phone browsers |
| Languages | English at launch; UI text prepared for Hindi and regional languages |
| Data retention | Set by Skyking policy; default proposal 7 years for complaint records |

# 7. Pan-India Branch Onboarding Approach

Onboarding happens at two levels: the branch is onboarded by Head Office, then the branch onboards its own staff.

## 7.1 Branch onboarding (Head Office)

- Branch master data. Collect branch code, name, address, city, state, region, serviceable pincodes, contact person and email in a template; bulk-import by CSV with validation.

- Create the branch in the CRM and assign it to a region.

- Nominate a Branch Admin (usually the branch manager). HO creates this first user, who receives an invitation.

- Branch Admin accepts, sets credentials and completes the branch profile.

- Training and go-live check (Section 7.4), then HO switches the branch to Live so L2 can assign complaints to it and the branch can register and forward complaints.

## 7.2 Staff onboarding (by the branch)

- Branch Admin opens Team → Invite staff, enters name, mobile and optional email, and picks a role (Branch Staff or Branch Admin).

- The invitee receives a link or one-time code by WhatsApp, SMS or email, valid for 72 hours.

- The invitee sets a password or signs in by OTP and sees only their branch’s work.

- Optional approval: Admin can require Head Office approval for new Branch Admins, or for every new staff member, during the pilot.

- Leavers: the Branch Admin deactivates a user in one click; open complaints return to the Branch Admin’s queue. Head Office can also suspend any branch user.

- Every invitation, role change and deactivation is audit logged. A branch cannot create users with Head Office roles.

## 7.3 Rollout waves

| Wave | Branches | Purpose | Exit criteria |
| --- | --- | --- | --- |
| Pilot | 2–3 branches in one region, mixed sizes, including one with weak connectivity | Prove workflow, SLA, chat and onboarding with real complaints | Two consecutive weeks with no severe defects; SLA breaches explained; branch staff confident without HO hand-holding |
| Wave 1 | Metro and high-volume branches | Largest share of complaints on the system early | Majority of volume on CRM; phone coordination for those branches stops |
| Wave 2 | Remaining regions, in batches by region | Scale onboarding with a repeatable playbook | Per-region go-live checklist signed |
| Wave 3 | Remaining and remote branches | Complete national coverage | 100% of active branches live; desktop CRM retired for complaints |

Batch sizes and dates are set after Phase 0, when the real branch count is known.

## 7.4 Per-branch go-live checklist

- Branch master data validated; pincode map confirmed

- Branch Admin identified and trained; at least two staff invited and active

- Device and internet check; mobile browser tested

- Branch staff trained on: register and forward a complaint, acknowledge, update, action taken, and the Head Office chat

- Test complaint completed end to end with HO

- Escalation contacts and notification numbers confirmed

- Go-live date agreed; HO hyper-care contact named

## 7.5 Training and support

- Short role-based guides and 5–10 minute videos; Hindi and key regional languages where branch staff need them.

- Live training in batches by region; recorded for new joiners.

- Two weeks of hyper-care after each wave, with a named support contact and a daily review of that wave’s open complaints.

- An in-app help link and a support channel for CRM issues, separate from complaint handling.

- Branch champions (one per region) who coach peers and feed back issues.

# 8. Planning and Development Roadmap

Per Key Decision 5, Phase 0 produces the approved roadmap and design; development (Phase 1 onward) starts only after Gate 0 sign-off. Durations are planning estimates for a team of the size in 8.3 and will be firmed up in Phase 0 once branch count, complaint volume and the legacy CRM data are known.

## 8.1 Phases

| Phase | Weeks | Main work | Output |
| --- | --- | --- | --- |
| 0. Discovery, planning and approval | 1–6 | Stakeholder interviews (HO, L1–L3, 3–5 branches); branch and volume census; legacy CRM data review; confirm Open Decisions; verify MSG91 API and webhooks; confirm email setup; finalize SLA policy; UX wireframes; sprint plan, budget and risk register | Approved requirements, design, roadmap and plan (Gate 0) |
| 1. Foundation | 7–10 | Environments, CI/CD, Alembic migrations; fix items in 3.1; hardened auth (refresh, MFA); region and branch model; branch-scoped access control with leak tests; complaint number sequence | Secure base that branch users can log into |
| 2. Workflow and SLA engine | 11–16 | Merge L0 into L1; new statuses; assign to branch; manual complaint creation for phone calls; de-escalation and full transition-rule enforcement; worker and queue; SLA policies, working-hours calendar, auto-escalation scanner, warnings, L3 breach alerts; notifications | Complaint moves L1 → L2 → branch → L3 with live timers (internal demo, Gate 2) |
| 3. Channels | 13–18 | MSG91 hardening and webhooks, full message history; email intake and threading; attachments; duplicate detection; customer acknowledgements | All three intake channels live in staging |
| 4. Branch module and HO chat | 14–19 | Branch queue and screens (mobile first); staff invitation and onboarding; Head Office thread and Help Desk channel; branch complaint registration and forwarding to Head Office; branch bulk import | Branches can work and talk to HO entirely in the system |
| 5. Reporting, hardening, UAT | 19–22 | Dashboards, ageing and SLA reports, Excel/PDF export; load test; penetration test; UAT with HO and pilot branches; training material; runbooks | UAT sign-off (Gate 3) |
| 6. Pilot | 23–26 | 2–3 branches live; daily review; fixes | Pilot exit report (Gate 4) |
| 7. Rollout | 27–40 | Wave 1 (27–30), Wave 2 (31–36), Wave 3 (37–40) with hyper-care after each | All branches live; desktop CRM retired for complaints (Gate 5) |

Headline: sign-off at about week 6, pilot-ready at about week 22 (roughly 5 months), national coverage at about week 36–40 (8–9 months). Phases 3 and 4 overlap Phase 2 by design.

## 8.2 Milestones and approval gates

| Gate | When | What must be true |
| --- | --- | --- |
| 0. Roadmap approval | End of week 6 | All items in 8.4 complete; Open Decisions closed; budget and team confirmed; sign-off in Section 13 |
| 1. Design freeze | Week 10 | Data model, role matrix and SLA rules frozen; changes go through change control |
| 2. Escalation demo | Week 16 | An end-to-end complaint, including an automatic 6-hour escalation (using a shortened test clock), demonstrated to steering group |
| 3. Go for pilot | Week 22 | UAT passed; no open critical or high defects; penetration test findings fixed; training ready |
| 4. Pilot exit | Week 26 | Pilot exit criteria in 7.3 met |
| 5. National completion | Week 40 | All active branches live; hand-over to support team |

## 8.3 Proposed team

| Role | Count | Note |
| --- | --- | --- |
| Project / delivery manager | 1 | Plan, risks, stakeholders |
| Business analyst / product owner (Skyking side) | 1 | Owns decisions and backlog priorities |
| Tech lead / architect | 1 | Owns design and quality |
| Backend engineers | 2 | Workflow, SLA, integrations |
| Frontend engineers | 2 | HO and branch UI |
| UX designer | 1 (part-time) | Wireframes in Phase 0, mobile branch flows |
| QA engineer | 1 | Automated and UAT |
| DevOps / cloud engineer | 0.5 | Environments, monitoring, security |
| Rollout and training lead | 1 (from week 18) | Onboarding waves |

If the existing team is smaller, the schedule extends rather than the scope silently shrinking.

## 8.4 Gate 0 checklist (what “complete and approved” means)

- Signed requirements (Sections 4 and 5) and closed Open Decisions (Section 12)

- Architecture and data model reviewed by the tech lead and Skyking IT

- Verified MSG91 API access and email mailbox access

- Real figures: branch count, staff count, daily complaint volume, peak hour

- Wireframes approved for L1, L2, L3 and Branch screens

- Detailed plan for Phases 1–5 (sprint level), budget, team named

- Risk register and test strategy approved

- Data migration scope agreed (9.5)

- Sign-off by the approvers in Section 13

# 9. Implementation Strategy

## 9.1 Delivery approach

Two-week sprints, each ending with a working demo to the product owner and a short feedback loop with a few HO users and two or three branch champions. Build in thin end-to-end slices, in this order: (1) a complaint moves between levels, (2) the clock escalates it, (3) it can be assigned to a branch, (4) branch and HO talk about it, (5) it arrives from email and WhatsApp. Reports and polish follow. This puts the riskiest logic (timers and permissions) in front of people first.

## 9.2 Environments and releases

Development, staging (a copy of production configuration for UAT and rehearsals) and production. Automated build, test and deploy; releases go out in off-peak windows with a rollback plan. Feature flags and per-branch enablement let us turn features on for the pilot branches before everyone.

## 9.3 Testing strategy

| Type | Focus |
| --- | --- |
| Unit and integration | Escalation and de-escalation rules, every transition in the matrix (5.9), permissions, assignment, intake adapters |
| SLA time tests | Simulated clock to test 6-hour thresholds, working hours, holidays, pauses, and repeated scanner runs |
| Access-scope tests | Prove a branch user can never see another branch’s complaints, chats or customers |
| Integration tests | MSG91 (sandbox or recorded payloads), email threading, notification delivery |
| Load and resilience | 3× expected peak; worker restart; MSG91 outage; duplicate webhook delivery |
| Security | Dependency scan, penetration test, secrets review |
| UAT | Scripted scenarios from real complaint types, run by HO and pilot branches |

## 9.4 Quality bar for pilot

No open critical or high defects; automated tests for every escalation path; monitoring and alerts active (including the SLA scanner heartbeat); backup restore rehearsed; runbook for support team.

## 9.5 Data migration and cutover from the desktop CRM

- Migrate: customer master (names, mobiles, addresses) and currently open complaints. Closed historical complaints are archived (exported and kept readable) rather than loaded, unless Phase 0 shows a strong need.

- Cleanse and de-duplicate customers by mobile number; dry-run the migration twice in staging.

- Cutover per wave: a branch stops using phone coordination for new complaints on its go-live date; open complaints at that branch are migrated that day. The desktop CRM is read-only for 30 days after each wave, then retired after Wave 3.

- No parallel double entry beyond the first week of the pilot.

## 9.6 Change management

Sponsor message from leadership explaining what changes and why; a simple rule that a complaint that is not in the CRM does not exist; branch champions; weekly adoption dashboard (branches live, staff active, complaints handled in system versus outside); feedback channel and monthly release notes.

## 9.7 Governance

Monthly steering group (sponsor, Operations head, IT head, project manager); weekly status report; change control for anything that alters scope, schedule or cost after Gate 1; risk register reviewed weekly; decision log maintained by the product owner.

## 9.8 Support model after go-live

Tier 1: branch champion and HO helpdesk for how-to questions. Tier 2: CRM support analyst. Tier 3: engineering on-call during working hours, with alerting for the SLA scanner and intake channels. Defect priorities and response times to be agreed in Phase 0.

# 10. Key Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| MSG91 API differs from the prototype’s assumptions, or webhooks are unavailable | Intake delays | Verify in Phase 0; keep polling fallback; record sample payloads |
| Branch adoption is low; staff keep using phone calls | Platform fails its purpose | Leadership mandate, champions, pilot first, adoption dashboard, hyper-care |
| 6-hour rule escalates too much (nights, holidays) and floods L2/L3 | Alert fatigue, ignored escalations | Working-hours clock, warnings at 80%, review thresholds after pilot |
| Poor connectivity or low-end devices at branches | Branch cannot respond in time | Mobile-first UI, lightweight pages, PWA, offline draft save, test in weak-network conditions |
| Unknown scale (branches, volume) | Wrong sizing and estimates | Census in Phase 0; load test at 3× |
| Scope creep | Delay and cost | Gate 1 design freeze, change control, Release 2 backlog |
| Data privacy and compliance gaps | Legal and reputational exposure | Legal review in Phase 0; access scoping, audit, retention policy |
| Silent failure of scheduler or channels | Missed escalations | Heartbeats, alerts, dead-letter handling, runbook |
| Prototype security shortcuts reach production | Breach | Fix list in 3.1 as a Phase 1 exit criterion |
| Key-person dependency in a small team | Schedule slip | Documentation, pair work, code reviews |
| Legacy data quality | Migration delay | Early profiling, limit migration scope (9.5) |

# 11. Success Measures (KPIs)

| Measure | Starting point | Target (to confirm with baseline from Phase 0) |
| --- | --- | --- |
| Complaints with an owner and a timer | Not tracked | 100% |
| Complaints handled fully in the CRM (not by phone or spreadsheet) | Not tracked | 95%+ of branch volume within 30 days of each branch’s go-live |
| Unattended complaints beyond 6 hours without escalation | Unknown | 0 (every breach escalates automatically) |
| Time to first response (L1) | Not tracked | Set from pilot baseline |
| Median and 90th-percentile resolution time | Not tracked | Reduce by an agreed percentage from baseline after 3 months |
| Share resolved at L1 / L2 / L3 | Not tracked | Track; aim to resolve more at L1 and L2 over time |
| Branches live | 0 | 100% of active branches by week 40 |
| Repeat or reopened complaints | Not tracked | Track and reduce |

We do not yet have baseline figures; the first task of the pilot is to measure them so targets are realistic.

# 12. Open Decisions and Information Needed

These must be settled in Phase 0 and recorded in the decision log.

| # | Question | Our recommendation |
| --- | --- | --- |
| 1 | Keep the prototype’s L0 (Support) as a separate level, or merge into L1 so there are exactly three levels? | Merge into L1 (agents plus team lead) |
| 2 | Does the 6-hour clock run 24×7 or only in working hours? What hours and holidays? | Working hours, configurable; shorter threshold for critical complaints |
| 3 | Is automatic escalation at 6 hours required, or should the system only alert and let a person escalate? (The brief says it “can” escalate.) | Automatic, with manual escalation also allowed at any time |
| 4 | How many branches, staff per branch, and complaints per day (average and peak)? | Needed for sizing, plan and budget |
| 5 | Who approves new branch staff: the Branch Admin alone, or Head Office as well? | Branch Admin alone, with HO approval for new Branch Admins |
| 6 | Who may close a complaint? Today only L3 and Admin. | L2 can close non-critical; L3 for critical |
| 7 | Should the customer confirm resolution, or does a complaint auto-close after a set period (for example 48 hours)? | Auto-close after 48 hours with a customer message; reopen on reply |
| 8 | Is there a booking or consignment system to integrate for automatic consignment lookup? | Plan for it in Release 2 unless Phase 0 shows it is essential |
| 9 | Which email provider and mailbox will receive complaints, and who administers it? | Dedicated mailbox with API or IMAP access |
| 10 | Branch languages and training needs; any branches with no reliable internet? | Hindi plus regional guides; identify weak-connectivity branches for the pilot |
| 11 | Data retention period and legal review of customer data handling | 7 years proposed; legal adviser to confirm |
| 12 | Decision 1 of the Key Decisions list is missing from the brief. | Please confirm |
| 13 | Budget, team and the cloud provider | Confirm at Gate 0 |
| 14 | Should some complaint categories go straight from the branch to L2, and may a branch resolve minor complaints locally without forwarding? | All complaints go to L1 first; local resolution off by default, enabled by Admin per category, with every such complaint still logged and visible to Head Office |

# 13. Approval and Sign-off

By signing, approvers confirm that the scope, workflow, architecture and roadmap in this document are accepted as the basis for development, subject to the closure of the open decisions above.

| Role | Name | Decision | Signature | Date |
| --- | --- | --- | --- | --- |
| Executive sponsor |  | Approve / Approve with changes / Reject |  |  |
| Head of Operations |  |  |  |  |
| Head of IT |  |  |  |  |
| Customer care / complaint handling lead |  |  |  |  |
| Branch representative |  |  |  |  |
| Project manager |  |  |  |  |
| Technical lead |  |  |  |  |